## Product Backlog
Product Name: | Exceptional Laptops and Supercomputers Always (ELSA) | [6 empty] | Complete Fields in Green!!!
Team ID: | VivifyHealth
| Team Member Name | [5 empty] | Initials | Student ID
Required | An Nguyen | [5 empty] | AN | 1001552004
Sprint # | Remaining | Completed This Sprint |  |  |  | Comment
0 | 10 |  |  |  | Total | Total number of features (in column H)
1 | 6 | 4 |  |  | 1 | Total features left at the end of Sprint #1
2 | 2 | 4 |  |  | 2 | Total features left at the end of Sprint #2
3 | 0 | 2 |  |  | 3 | ...and so on
4 | 0 | 0
5 | 0 | 0
Note: Priority and specs for unfinished Features is subject to change at the end of each sprint at the whim of the Product Owner
Additional features may be proposed by the student but must be approved by the Product Owner in writing
Sprints
Feature ID | Priority | Required | Bonus | Est | Planned | Status | As a... | I want to... | So that I can… | Notes
CUST | 1 | 1 |  | 3 | 1 | Finished in Sprint 1 | Sales Staff | Remember each customer’s name and contact info | Ship them products repeatedly | UPDATE: Make Dialog to insert customers more user-friendly by adding entry boxes
OPT | 2 | 1 |  | 8 | 1 | Finished in Sprint 1 | Inventory | Maintain a list of options for a desktop (e.g., disk, RAM, CPU) | Select them when designing a new desktop product | UPDATE: Make Dialog to insert peripherals more user-friendly by adding buttons, add specific buttons for peripherals
DESKT | 3 | 1 |  | 8 | 1 | Finished in Sprint 1 | Sales Staff | Define a new desktop configuration from options | Can quickly customize products for my customers
ORDER | 4 | 1 |  | 13 | 1 | Finished in Sprint 1 | Sales Staff | Associate a customer with one or more desktops into an order | Keep track of who has bought what
VIEW | 3 | 1 |  |  | 2 | Finished in Sprint 2 | Inventory | Display information pertaining to the store | Keep track of customers/inventory
INSERT | 2 | 1 |  |  | 2 | Finished in Sprint 2 | Customer | Define new information pertaining to the store | Add new customers/orders/products
ABOUT | 4 | 1 |  |  | 2 | Finished in Sprint 2 | Sales Staff | Provide information about the ELSA company | Inform customers about our products
MENU | 1 | 1 |  |  | 2 | Finished in Sprint 2 | Customer | Transition to Graphical User Interface | Interact with software more easily
SAVE | 1 | 1 |  |  | 3 | Finished in Sprint 3 | Inventory | Save store informaiton into a file | Save data for later use
OPEN | 2 | 1 |  |  | 3 | Finished in Sprint 3 | Inventory | Open a file containing store information | Reuse old data saved

## Sprint 01 Backlog
Sprint # | 1 |  | Complete Fields in Green!!!
Start on | 2020-03-03 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2020-03-24
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 16
Day 1 Left | 14 | 2
Day 2 Left | 9 | 5
Day 3 Left | 9 | 0
Day 4 Left | 3 | 6
Day 5 Left | 0 | 3
Day 6 Left | 0 | 0
Day 7 Left | 0 | 0
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 | CUST |  | Write the Customer class | Completed Day 1 | Test each class and method as it is written
2 | CUST |  | Write operator<< for Customer | Completed Day 1 | Commit and push AT LEAST once every class or update
3 | CUST |  | Write Store::add_customer, num_customers, and customer | Completed Day 2
4 | OPT |  | Write the Options class sans to_string | Completed Day 2
5 | OPT |  | Write Options::to_string and its operator<< | Completed Day 2
6 | OPT |  | Write Store::add_option (to Store), num_options, and option | Completed Day 4
7 | DESKT |  | Write the Desktop class with add_option method | Completed Day 4
8 | DESKT |  | Write the Desktop::price method | Completed Day 2
9 | DESKT |  | Write operator<< for Desktop | Completed Day 2
10 | DESKT |  | Write Store::new_desktop, add_option (to desktop), num_desktops, and desktop | Completed Day 4
11 | ORDER |  | Write the Order associative class and constructor | Completed Day 4
12 | ORDER |  | Write Order::add_product | Completed Day 4
13 | ORDER |  | Write Order::price | Completed Day 5
14 | ORDER |  | Write Store::new_order, add_desktop, num_orders, and order | Completed Day 4
15 | ORDER |  | Integrate and test with cse1325_prof/elsa/sprint_1/main.cpp | Completed Day 5
16 | ORDER |  | Ensure ALL CODE is on GitHub by deadline! | Completed Day 5
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 02 Backlog
Sprint # | 2 |  | Complete Fields in Green!!!
Start on | 2020-03-24 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2020-03-31
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 16
Day 1 Left | 16 | 0
Day 2 Left | 13 | 3
Day 3 Left | 13 | 0
Day 4 Left | 9 | 4
Day 5 Left | 2 | 7
Day 6 Left | 0 | 2
Day 7 Left | 0 | 0
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 | MENU |  | Add View and Insert menus to the Menu Bar | Completed Day 2
2 | MENU |  | Add menu items to View and Insert menus | Completed Day 2
3 | MENU |  | Connect Activate signals to observer methods | Completed Day 2
4 | MENU |  | Write Mainwin::get_double, get_int, get_string | Completed Day 4
5 | MENU |  | Write Mainwin::set_data, set_msg | Completed Day 4
6 | INSERT |  | Write Mainwin::on_insert_customer_click() | Completed Day 4
7 | VIEW |  | Write Mainwin::on_view_customer_click() | Completed Day 4
8 | INSERT |  | Write Mainwin::on_insert_peripheral_click() | Completed Day 5
9 | VIEW |  | Write Mainwin::on_view_peripheral_click() | Completed Day 5
10 | MENU |  | Implement Status Bar | Completed Day 6
11 | INSERT |  | Write Mainwin::on_insert*() | Completed Day 5
12 | VIEW |  | Write Mainwin::on_view*() | Completed Day 5
13 | ABOUT |  | Create/Find company logo | Completed Day 5
14 | ABOUT |  | Write Mainwin::on_about_click() | Completed Day 5
15 | MENU |  | Integrate and test with code from Sprint 01 | Completed Day 5
16 | MENU |  | PUSH code to Github by deadline! | Completed Day 6
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 03 Backlog
Sprint # | 3 |  | Complete Fields in Green!!!
Start on | 2020-03-31 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2020-04-07
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 12
Day 1 Left | 12 | 0
Day 2 Left | 12 | 0
Day 3 Left | 12 | 0
Day 4 Left | 9 | 3
Day 5 Left | 6 | 3
Day 6 Left | 0 | 6
Day 7 Left | 0 | 0
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 | SAVE |  | Add save(std::ostream& ost) to each class | Completed Day 4
2 | SAVE |  | Add Constructor(std::istream& ist) to each class | Completed Day 4
3 | OPEN |  | Add menu items to File: Open, Save and Save As | Completed Day 4
4 | OPEN |  | Write Mainwin::on_open_click() and Mainwin::on_save_as_click() | Completed Day 5
5 | SAVE |  | Write Mainwin::on_save_click() | Completed Day 5
6 | SAVE |  | Write Customer::save(ostream&) and Customer::Customer(istream&) | Completed Day 5
7 | SAVE |  | Write Order::save(ostream&) and Order::Store(istream&) | Completed Day 6
8 | SAVE |  | Write Options::save(ostream&) and Options:Options(istream&) | Completed Day 6
9 | SAVE |  | Write Desktop::save(ostream&) and Desktop::Desktop(istream&) | Completed Day 6
10 | SAVE |  | Write Store::save(ostream&) and Store::Store(istream&) | Completed Day 6
11 | OPEN |  | Build and test error handling | Completed Day 6
12 | SAVE |  | PUSH code to Github by deadline! | Completed Day 6
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 04 Backlog
Sprint # | 4 |  | Complete Fields in Green!!!
Start on | 2020-04-07 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2020-04-21
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 8
Day 1 Left | 8 | 0
Day 2 Left | 8 | 0
Day 3 Left | 8 | 0
Day 4 Left | 4 | 4
Day 5 Left | 1 | 3
Day 6 Left | 1 | 0
Day 7 Left | 1 | 0
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 | CUST |  | Update Mainwin::on_insert_customer_click() | Completed Day 4
2 | OPT |  | Write Ram::Ram(std::string…int gb) and Ram::~Ram() | Completed Day 4
3 | OPT |  | Override Options::to_string method with Ram::to_string() | Completed Day 4
4 | OPT |  | Override Options::save(std::ostream&) method with Ram::save(…) | Completed Day 4
5 | OPT |  | Write Ram::Ram(std::istream&) | Completed Day 5
6 | INSERT |  | Update Mainwin::on_insert_peripheral_click() | Completed Day 5
7 | OPT |  | Write Mainwin::on_ram_click() | In Work
8 | OPT |  | Write Mainwin::on_other_click() | Completed Day 5
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 05 Backlog
Sprint # | 5 |  | Complete Fields in Green!!!
Start on | 2020-04-21 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2020-04-28
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 1
Day 1 Left | 1 | 0
Day 2 Left | 1 | 0
Day 3 Left | 1 | 0
Day 4 Left | 1 | 0
Day 5 Left | 1 | 0
Day 6 Left | 1 | 0
Day 7 Left | 1 | 0
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 |  |  | --> Add tasks to complete each feature for this sprint
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84